## Slide 1: CEN/WS XBRL PT kick-off meeting
9 August, 2012
Background, formalities and working mode

## Slide 2: Contents
Objectives
Formalities and regulations
Document handling and drafting
Timeline
Mode of operation
Time schedule and planning
Start of work

## Slide 3: Objectives
Parallell track
  Fulfillment PT contract with CEN / NEN
  Supply drafts for handling in the normal standardisation track
PT Expert contract (with NEN)
  Defines the formal contract fulfilment and obligations
  Contract timing
  Deliverables (incl. reports)
Working group is the main interface
  Work item timing
  Comments, supervision, approval for TC-handling

## Slide 4: Formalities
The contract is with NEN (no WS or WG involvement)
  Formal delivery to NEN (CEN/WS XBRL secretariat)
  All contractual questions to NEN
Alignment with CEN consensus processes
  CEN/WS XBRL meetings and time schedule
Monitoring performed by the WG convenor
  WG convenor is first contact point

## Slide 5: Format and drafting rules
Drafting rules
  The deliverable shall be drafted using the STD template (v2.4), and
  according to CEN drafting rules (CEN directive part 2)
Figures
  Figures in both revisable (EPS) and published format (TIFF)
  Black and white or greyscales (no colours)
Guides & Tools
  Drafting CEN ISO deliverables - Common rules and elements
Questions concerning the format and drafting rules can be directed to the TC secretary.

## Slide 6: Timeline
Deadlines
2012-12 - Interim report to EC incl. draft CWAs
2013-07 - 3 months Public consultation
2014-02 - Final report to EC incl. approved CWAs
Drafting
WG review
Comments resolution
Public consultation
Comments resolution
Voting
Dec
2013
Aug 2012
Sep
2013
Spring 2013
1
2
3
1
2
3
Project Team input

## Slide 7: Mode of operations
1 Draft (WD)
TC secretary
2 PT presentation in WG
4 Public consultation
3 Draft Rev1
5 Final draft
TC secretary
TC secretary
6 Decision
Steps 1-3 can be repeated until final draft for public consultation
Discussion, changes, decision
PT prepares first draft
PT produces a second draft
3 months public consultation
PT produces final draft
Approval of CWA by CEN/WS XBRL members

## Slide 8: CEN/WS XBRL planning and meetings
CEN/WS XBRL, Winter 2012
CEN/WS XBRL, Spring 2013 (face-to-face meeting)
CEN/WS XBRL, Winter 2013
CEN/WS XBRL, Spring 2014
PT Working Drafts must be available at least 2 weeks in advanced of CEN/WS XBRL meetings

## Slide 9: Start of work
1) Sign contract between PT expert and NEN
2) Work Plan (prepared by the PT)
Content Work Plan (most of this information is already available in the ToR)
  Scope and objective
  Approach, methodology and work breakdown
  Roles and tasks of each PT member
  Time plan incl. drafting, reviewing and dissemination
  Interaction, mode of collaboration and reporting
    Within the PT, With working group, With stakeholders
  Preliminary listing of issues and priorities
  Draft table of contents
3) Start drafting deliverable(s) according to ToR